## Phase Overview
GharSetu — Project Timeline
Delivery companion to Solution_Overview.docx. Same order, same reference: Close the Gaps → New Features → Integration, VAPT & Release.
Time is in working days. Day 1 = first working day after the client signs off the Solution Overview + prototype. Built by multiple AI agent teams in parallel — total: 8 working days.
Phase | Duration | Items | What happens
A — Close the Gaps | Day 1 – Day 3 | 9 | Repair every broken or missing area in the current system, module by module, in Solution-Overview order. Multiple agent teams work in parallel each day.
B — New Features | Day 4 – Day 6 | 14 | Build the new features in Solution-Overview order: Per-Room Leasing, Impersonation, Delegation, Visitor Management, then the Organization Management (SAAS) layer — parallelised across agent teams.
C — Integration, VAPT & Release | Day 7 – Day 8 | 4 | Whole-platform regression, a consolidated security assessment (VAPT), client UAT, and sign-off.
Key Milestones
Milestone | By
Project start | Day 1
Phase A complete — all gaps closed | Day 3
Phase B complete — all new features built | Day 6
Full-platform VAPT complete | Day 7
Client sign-off (project complete) | Day 8
Notes
• Time is shown in working days (Day 1 … Day N), not calendar dates. Day 1 is the first working day after the Solution Overview + prototype are signed off; exact dates are fixed once the start date is agreed.
• No prototype/design phase is included — design is already done; this schedule starts at build.
• Build work is done by multiple autonomous AI agent teams (Backend, Frontend, DBA, QA, Security) working IN PARALLEL — up to 6 work items run on the same day. This is why the whole engagement is ~8 working days, not weeks.
• Every feature is built AND tested (automated + manual) AND VAPT-checked by its agent team within its day; a consolidated full-platform VAPT then runs in Phase C before UAT.
• Colour key: blue = Close the Gaps (Phase A) · saffron = New Features (Phase B) · grey = Integration / VAPT / Release (Phase C).

## Schedule
#
Schedule — Close the Gaps, then New Features, then Release
One row per work item, in Solution-Overview order. Items sharing a Day run in parallel across different AI agent teams. Each feature is built, tested (auto + manual) and VAPT-checked within its day.
Blue = Close the Gaps · Saffron = New Features · Grey = Integration / VAPT / Release.
# | Day | Phase | Module / Area (per Solution Overview) | Work Item | Includes (per item) | AI Agent Team
1 | Day 1 | A | Users & Access | User Management — create/edit users, role-restricted creation. | Build · Automated tests · Manual QA · VAPT check | Backend · Frontend
2 | Day 1 | A | Properties & Units | Property Management, Unit Management, Reassign Property Manager — complete end-to-end. | Build · Automated tests · Manual QA · VAPT check | Backend · Frontend
3 | Day 1 | A | Settings | Late-Fee Rate, Grace Period, Rent-Change Notice Window — Admin-tunable. | Build · Automated tests · Manual QA · VAPT check | Backend · Frontend
4 | Day 1 | A | Master Data Management | Amenities, Maintenance Categories — Admin-managed; in-use entries protected. | Build · Automated tests · Manual QA · VAPT check | Backend · Frontend
5 | Day 2 | A | Leases & Tenants | Lease Creation, Lease Renewal, Lease Termination, Rent Change Schedule, Tenant Creation. | Build · Automated tests · Manual QA · VAPT check | Backend · Frontend
6 | Day 2 | A | Maintenance Requests | Request Detail View, Status Lifecycle (Close & Reopen), Priority Change During Request, High-Volume Alert. | Build · Automated tests · Manual QA · VAPT check | Backend · Frontend
7 | Day 2 | A | Rent Collection | Record Payment, Partial Payment Tracking, Period Filters. | Build · Automated tests · Manual QA · VAPT check | Backend · Frontend
8 | Day 3 | A | Dashboard | Admin, Property Manager, Maintenance Team and Tenant dashboards. | Build · Automated tests · Manual QA · VAPT check | Frontend · Backend
9 | Day 3 | A | Server Hardening | Access control, Data integrity, Concurrency, Observability, Performance, Security. | Build · Automated tests · Manual QA · VAPT check | Backend · Security
10 | Day 4 | B | Leases & Tenants | Per-Room Leasing — rooms under units; unit-wise & room-wise lease types; shared areas; room/shared-area maintenance scope. | Build · Automated tests · Manual QA · VAPT check | Backend · Frontend · DBA
11 | Day 4 | B | Users & Access | Impersonation — Admin signs in as an Org user; actions audited against the Admin. | Build · Automated tests · Manual QA · VAPT check | Backend · Frontend
12 | Day 4 | B | Users & Access | Delegation — date-range task delegation to PM / Maintenance; revocable; audited against the delegate. | Build · Automated tests · Manual QA · VAPT check | Backend · Frontend
13 | Day 4 | B | Visitor Management | Tenant registers expected visitors; PM / Admin approve, deny, check-in / check-out. | Build · Automated tests · Manual QA · VAPT check | Backend · Frontend
14 | Day 5 | B | Organization Management | Multi-organization migration — convert to multi-org; migrate existing data into a "default" organization. | Build · Automated tests · Manual QA · VAPT check | Backend · DBA
15 | Day 5 | B | Organization Management | Public organization sign-up — Sign Up page and sign-up request flow. | Build · Automated tests · Manual QA · VAPT check | Frontend · Backend
16 | Day 5 | B | Organization Management | Public website + legal pages — marketing site with plans; Contact, Privacy Policy, Terms & Conditions. | Build · Automated tests · Manual QA · VAPT check | Frontend
17 | Day 5 | B | Organization Management | Super Admin role — review/approve sign-ups; provision org and auto-create its first Admin. | Build · Automated tests · Manual QA · VAPT check | Backend · Frontend
18 | Day 6 | B | Organization Management | Subscription Plan catalogue — Basic / Standard / Premium; assign or change plan per org; user caps. | Build · Automated tests · Manual QA · VAPT check | Backend · Frontend
19 | Day 6 | B | Organization Management | Organization lifecycle — view, deactivate, reactivate any organization. | Build · Automated tests · Manual QA · VAPT check | Backend · Frontend
20 | Day 6 | B | Organization Management | Invoicing — Super Admin manages invoices for every organization. | Build · Automated tests · Manual QA · VAPT check | Backend · Frontend
21 | Day 6 | B | Organization Management | Legal pages & contact queries — manage legal content; view and triage contact queries. | Build · Automated tests · Manual QA · VAPT check | Backend · Frontend
22 | Day 6 | B | Organization Management | Platform-level Master Data — City, State, Payment Methods managed centrally for all orgs. | Build · Automated tests · Manual QA · VAPT check | Backend · Frontend
23 | Day 6 | B | Organization Management | Admin Organization view — Admin page showing own org details, plan and invoices. | Build · Automated tests · Manual QA · VAPT check | Frontend · Backend
24 | Day 7 | C | Release | Integration & end-to-end regression — full automated + manual pass across all modules. | Automated + manual regression (all modules) | QA · Backend · Frontend
25 | Day 7 | C | Release | Full-platform VAPT — OWASP Top 10, role-scope leak audit, payment-write authorization, auth/session. | Security assessment — OWASP, role-scope, payments, auth | Security
26 | Day 8 | C | Release | UAT deployment & client acceptance testing. | Client acceptance testing on UAT environment | PM · QA · Client
27 | Day 8 | C | Release | Bug closure, re-test and final client sign-off. | Fixes · re-test · client sign-off | All agents